## Guidance
This form should be read in conjuction with SLP 2.3.2.7_02. Supporting guidance for each heading in the form is provided here.
SLF 2.3.2.7_02 Heading | Supporting Guidance
Description | Each system should be broken down to the appropriate level of component granularity by considering the consequences of the item(s) not conforming to specification at point of use. Consider individual items and/ or assemblies as appropriate. The level of granularity should also consider the oversight and assurance required for lifetime spares.
Item no. | Detail the scope to be manufactured / supplied in the procurement section, including plant item numbers (if known / applicable), quantities required, the relevant drawings / specs (note: there generally will always be some sort of relevant specification such as SL ES spec, a British standard or project document), the selected supplier (if known at this point)
Plant Item/ Component no.
Description
Drawing ref.
Specification
Vendor (if known)
Risk Assessment | Determine the consequences of failure for the specified component.
Nuclear / Radiological Safety | Use SFC 1, SFC 2, SFC 3, SF, SM, SRE, NP or EE.
Conventional Safety | Use very high (VH), high (H), medium (M), low (L) or no risk (N/A)) based on the assessed the risk as required by the relevant legislation, e.g. the Control of Substances Hazardous to Health Regulations (COSHH), Dangerous Substances and Explosive Atmospheres Regulations (DSEAR), the Supply of Machinery (Safety) Regulations and the Control of Major Accident Hazards Regulations (COMAH) and the relevant practices in SLMS Topic Area 2.04. Standards and guidance may also be relevant, e.g. Engineering Guides Series 7000 and for machinery, BS EN ISO 12100 - Safety of machinery - General principles for design - Risk assessment and risk reduction.
Environmental Risk | Use E1, E2 or E3 Refer to Section 1.2 in SLSP 1.02.14.02 "Potential Impact under Fault Conditions".
Operational Risk | Consider throughput, reliability, availability and maintainability (TRAM) impact of the component. Use very high (VH), high (H), medium (M), low (L) or no risk (N/A)).
Security Risk | Based on the consequences of physical or cyber security of failure. Use very high (VH), high (H), medium (M), low (L) or no risk (N/A)).
Grey Market Risk | Identify if the orignal equipment manufacturer is known
Business Risk | Consider financial, programme, or commercial consequences Use very high (VH), high (H), medium (M), low (L) or no risk (N/A)).
Quality Grade | Use 1, 2, 2P, 3, or 4 should be specified where SL direct contract award for the commercial and contract aspects. Otherwise insert N/A. Include justification in supporting comments when using QG2P
Requirements | The requirements are specified based on the risk assessment and the relevant standards, e.g. British, International or Engineering Standards. If there are additional requirements, insert these in additional columns. For each requirement use the following convention is used:
Yes (SL) | For verification by SL
Yes (SL/MC) | For verification by SL & Main Contractor Inspector
Yes (MC) | For verification by Main Contractor Inspector
Yes (Other) | For verification by Other organisation as specified
N/A | Not applicable
UKCA marking | CE/UKCA marking is required for many products that are available for sale within the UK and European Community. A valid CE/UKCA mark: • Demonstrates that the manufacturer has checked and that the products meet safety, health or environmental requirements. • Provides a visible indicator of a product’s compliance with legislation. Where materials and/or equipment are being used in a nuclear context it is particularly important to ensure that all CE/UKCA marking requirements have been complied with and that the item(s) bear the required marking to demonstrate that the specified requirements or standards have been fully met. Will the product require CE/UKCA marking? If yes, is it to be issued by the supplier? Who owns the technical file? NS Toolbox Talk 15 and SLSP 1.02.07.19 provides further guidance.
Start Up Meeting | Where scope of supply is complex, has high risk assessment factors, or if the contractor is new to the nuclear industry or has not been involved in nuclear work in the last three years, the Delivery Organisation must ensure a Start up meeting is arranged with all key suppliers. The purpose of the meeting is to ensure that the contractor is aware of all delegated duties under the contract, any SL related problems/activities and to introduce personnel involved in the contract. This can ensure the deliverables meet expectations and are fit for purpose and improve collaborative working with the supply chain to ensure that quality requirements are meet. Refer to SLP 3.02.07 for further information. This should include a specification awareness brief to take the contractor through each clause of the specification to ensure they have a full understanding of the requirements.
Verification and Acceptance of Contractor Design | Does the design require to be submitted and acceptance prior to fabrication, manufacture or installation? Are hold points required for verification and acceptance to effectively release and install plant and equipment? Define these as required in supporting comments.
Approval of Supplier Quality Plan/ Inspection & Test Plan/ Inspection Check List | Confirm whether approval of the Supplier Quality Plan, Inspection & Test Plan/ Inspection Check List is required by SL. Identify whether specific hold points are required to support verification of requirements.
Relevant Nuclear Safety Tool Box (NSTB) | Use a risk-based approach to identify the appropriate Nuclear Safety and Specification Awareness briefing requirements. All Sellafield Ltd and contractor project induction courses must include the appropriate level of Nuclear Safety and Specification Awareness material, Sellafield Ltd Nuclear Safety briefs can be obtained from the SL and Supply Chain Quality Hub Group. https://slportal.ssa-intra.net/pub/SC005/00086/Documents/Forms/Training.aspx
Review of Competent Person Qualifications | Qualifications provide evidence that the persons completing the activity (i.e. welders) are qualified.
Review of Procedures i.e. Weld, Painting, NDT or Test Procedures Prior to Fabrication | Approved procedures provide evidence that the contractor is capable of achieving the specified weld, paint and NDT requirements prior to fabrication. Refer to NS Toolbox Talk 006, 20, 22, 31, 42 [Welding] Refer to NS Toolbox Talk 007, 32, 33, 34, 38, 39 [Paint]
Material Control | Is material certification and traceability required to provide technical confirmation and the documented history of materials used in a product, ensuring they meet specified quality, safety, and regulatory standards. · If materials which are the incorrect grade or type, or use out of specification or counterfeit material, then the equipment produced is not as per the design intent and may fail in service which could lead to a nuclear safety or conventional safety event, or in some cases both. · Only through effective and accurate certification can it be confirmed that the materials used are as per design intent and will not pose a threat to the safe operation of the facilities. NSTB 4 & 11
Interim Inspection | Identify any interim inspection or witness hold points required at specific, intermediate stages of the manufacturing process, before the final completion of the unit. It serves as a proactive measure to verify that partially completed components, assemblies, or processes adhere to design, code, and quality standards (such as ASME, ISO) before they are covered or sealed by further fabrication steps.
Specialist Testing | For example: PT – Pressure Testing LT – Load Testing CT – Cube Testing LK - Leak Testing CFSI - define scope of testing required if Counterfeit Fraudulent or Suspect Items
Acceptance Test | For example: FAT – Factory Acceptance Test SAT – Site Acceptance Test CAT – Client Acceptance Test
Documentation | For example: CofC – Certificate of Conformity DofC – Declaration of Conformity O&M – Operation & Maintenance Manual (inc Original Equipment Manuals) CC – Calibration Certification The requirements for specific documentation should also be defined in Life Time Record Strategy. Refer to SLSP 2.15.05
Final Inspection (identify all that apply) | Identify requirements for final Inspection. · Performed at Contractor's/Supplier’s Works · On receipt at Lilyhall Stores · Inspection on receipt
Review of LTR's prior to Release | Confirm whether the main contractor, and their relevant suppliers, conduct their own review and verification of the LTR pack, prior to submittal to Sellafield Ltd. Upon receipt of the LTRs it is the remit of the integrated team to ensure technical, quality and admin checks are all conducted on each section of each LTR pack. Refer to SLSP 2.15.05
Product Release Certificate Required, e.g. 5059 | Confirm whether Inspection and Certification Group (or other Inspection Authority) needs to verifies the conformity of the product or service at interim and final stage against the acceptance criteria prior to release of plant and equipment or products from a manufacturer’s works. This is N/A for site installation, SLF 2.15.02.04 Intermediate Certificate of Inspection Form 5199 can be used where equipment is being sent elsewhere (i.e. for integration for modular build) SLF 2.15.02.05 Final Certificate of Inspection Form 5059 is used for delivery directly to Sellafield.
Inspection of Packing/ Preservation | Confirm whether inspection of packaging or specific preservation requirements are required for future storage following delivery to Sellafield.
Other | Other inspection or test requirements can be added as required for the scope of supply. Define these in the heading with supporting comments as required.
Supporting Comments/ Justification | The supporting comments section is useful to capture additional notes which assist the interpretation of the form (such as: noting any additional supporting documents, any Q02P supporting comments, specific certification needs, testing arrangements or any missing scope to capture a later date / revision).
Confirmed by: | Once the content of the form has been fully agreed by all relevant stakeholders, the form is then to be checked and approved in accordance with SLP 1.02.42 and issued to Project Document Control in accordance with SLP 4.09.108.

## Form
Project/Job Title: |  |  | DNWP0003 DNWP Call Off Scope_SSRF_v1 |  |  |  |  | Document Title: |  |  | Quality Requirements Risk Assessment – SSRF
Project/Job Number: |  |  | 35 05782 |  |  |  |  | Document Number: |  |  | RA/B88/PROJ/00031 (Revision B)
[8 empty] | Date: |  |  | 2026-10-28
DESCRIPTION | [5 empty] | RISK ASSESSMENT | [8 empty] | REQUIREMENTS
Item no. | Plant Item/ Component no. | Description | Reference(s) | Vendor (if known) | Quantity | Nuclear / Radiological Safety | Safety Case Function Category | Conventional Safety | Environmental Risk | Operational Requirements (TRAM) | Security | Grey Market (is Original Equipment Manufacturer (OEM) known) | Business Risk | Quality Grade | UKCA marking | Start Up Meeting | Verification and Acceptance of Contractor Design | Approval of Supplier Quality Plan/ Inspection & Test Plan/ Inspection Check List | Enter type | Relevant Nuclear Safety Tool Box Ref. | Review of Competent Person Qualifications | Review of Procedures i.e. Weld, Painting, NDT or Test Procedures Prior to Fabrication | Material Control | Interim Inspection | Specialist Testing | Manually enter applicaple codes | Acceptance Test | Manually enter applicaple codes | Documentation | Manually enter applicaple codes | Final Inspection | Review of LTR's prior to Release (N/A site installation) | Product Release Certificate Required, e.g. 5059 (N/A site installation) | Inspection of Packing/ Preservation | Other (please specify)
Procurement / Fabrication:
1 | DNWP0003 | 1.01 Remote activation of Krantz butterfly valve: 1) Source and fit components for the Krantz to allow remote control of Krantz butterfly valve. |  | A2R |  | Med | SF | Low | E3 | Low | Low | N/A | Med | QG03 | Yes | N/A | Yes (MC/SL) | Yes (MC/SL) | ICL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CofC DofC | N/A | Yes (MC/SL) | N/A | N/A | N/A
2 | DNWP0003 | 1.02 Quickchange shielded box: Offsite concept/testing and manufacture. |  | A2R |  | Med | SF | Low | E3 | Med | Low | N/A | Med | QG03 | No | N/A | Yes (MC/SL) | Yes (MC/SL) | ICL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes (MC) | FAT | Yes (MC) | COC | N/A | Yes (MC/SL) | N/A | N/A | N/A
3 | DNWP0003 | Procurement of laser head - testing and possible programming. |  | A2R |  | Low | N/A | Low | E3 | Low | Low | Low | Low | QG04 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes (MC) | CofC DofC | N/A | Yes (MC/SL) | N/A | N/A | N/A
4
5
Site Installation:
1 | DNWP0003 | Filter Change and Analysis for Krantz MRHF / MSCF: 1) Change 2 x RH 13 filters & 1 H14 filter. 2) Survey the activity on the single H14 filter at the front and the back. 3) Swab the vent exhaust point. |  | A2R |  | Med | SF | Low | E3 | Low | Low | N/A | Low | QG03 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
2 | DNWP0003 | 1.01 Install / terminate cabling; commission and amend schematics and OI for Krantz butterfly valve. |  | A2R |  | Low | SF | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
3 | DNWP0003 | 1.02 Krantz PVC bag with quickchange shielded box to be installed/commissioned and tested. |  | A2R |  | Low | SF | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | Yes (MC/SL) | ICL | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes (SL) | SAT | Yes (MC/SL) | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
4 | DNWP0003 | New enclosure in bulky item area - Adhoc support where required, this may include lifting plans, and delivery/loading plans and other supporting documentation |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
5 | DNWP0003 | Subchange modifications including contamination control by having a fit for purpose sub change to allow contamination to be caught in C3 area rather than C/1 areas and build a shielding area for egress out of the area. |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
6 | DNWP0003 | Develop operational capability (operator training) - to allow for self-sustainability for SL to deliver in house. Leconfield training with robotics - onsite familiarisation - Fanuc (Coventry). Min 4 operators to be trained. SL maintenance team to be trained on PVC welding. |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | Training & Qualifications | N/A | N/A | N/A | N/A | N/A
7 | DNWP0003 | Alternative access/egress skip route through product load - Engineering support and LOAP required |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
8 | DNWP0003 | Contam rollback & improvements (Line 300, bulky items, waste sort) - Supply and installation |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
9 | DNWP0003 | Pendant for Crane - Lifting plans to be updated for this. |  | A2R |  | Low | SF | Low | E3 | Low | Low | N/A | Low | QG04 | Yes | N/A | Yes (MC/SL) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | Yes (MC/SL) | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
10 | DNWP0003 | Laser head replacement - laser head joint installation with SL |  | A2R |  | Low | SRE | Low | E3 | Low | Low | N/A | Low | QG04 | Yes | Yes (MC/SL) | Yes (MC/SL) | Yes (MC/SL) | QP | N/A | N/A | N/A | Yes (MC) | Yes (MC) | N/A |  |  | N/A | Yes (MC/SL) | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
11 | DNWP0003 | Inline filters in laser cooling system - potential for call on Supply chain for support to Sellafeild. |  | A2R |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | Yes | Yes (MC/SL) | Yes (MC/SL) | Yes (MC/SL) | QP | N/A | N/A | N/A | Yes (MC) | Yes (MC) | N/A |  |  | N/A | Yes (MC/SL) | IMS - Installation Method Statement Redline/As Built Drawings | Yes (SL) | N/A | N/A | N/A | N/A
12 | DNWP0003 | Gripper modifications - TKE required for software programming for utilisation of gripper for custom cuts. |  | TKE |  | Low | N/A | Low | E3 | Low | Low | N/A | Low | QG04 | No | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | IMS - Installation Method Statement Redline/As Built Drawings | N/A | N/A | N/A | N/A | N/A
Supporting Comments/ Justification (inc. factors considered, ref. SLP 2.3.2.7_02, Appendix 1)
Revision B initiated 28/10/2026. Quality grades modified and LTR requirements defined against QD/B88/PROJ/00024. Revision A initiated 18/03/2026. Preliminary scope defined to ensure contractual application of relevant Quality Grade. Laser head replacement - laser head joint installation with SL. Pre- Inspection Meeting will depend on the replacement being significantly different from the exisiting item.
Confirmed By |  | Position (*Delete or add as appropriate) |  |  | Date
Christopher Paine |  | Delivery Manager (SL)
Kyle McNicol |  | Quality Engineer (SL)
Michelle Beattie |  | DNWP Quality Lead (A2R)
Ellie Jenkinson |  | Certification Coordinator (A2R)
Stephen Harris |  | Reliability Engineer (SL)
Marie Maxwell |  | Quality Manager (SL)